# Interactive Multimedia Production Task List

# Analysis

- Hold preliminary concept meetings (determine cost, content, market, technology, media, goals, skills needed.)

- Write concept paper

- Assign roles and responsibilities to team members

- Determine Preliminary Budget (all aspects from initial planning through field test and final corrections)

- Determine Schedule to be reevaluated on a regular basis.

# Content/Prototype Development

- Hold kick off meeting

- Hold content analysis/outline meeting

- Develop detailed outline

- Identify outside vendors to bid with

- Develop design document (includes: rough nav, media to be used amount of text, graphic needs, interactivity, palette, recurring elements, hierarchy, metaphors, High-level flow chart, Determine separate versions (Text v. Sound, geographic region, staff level)

- Develop detailed Budget

- Review Schedule

- Send out RFP/design document to potential vendors  (include detailed deliverables)

- Review proposals from vendors

- Revised bids from select vendors (if necessary)

- Select Vendor

- Write Contract

- Get signed contract

- Review Budget

- Review Schedule

- Hold Art/Content meeting with all members of team and outside vendors.

- Deliver rough content draft

- Build screen mockups (use longest and shortest pages for comping)

- Determine art for interface (Navigation buttons, page design, etc.)

- Determine art for content (identify art needed, collect scan existing art, identify sources of other art, commission illustrations, etc.)

- Finalize detailed storyboard and flow chart (includes all elements: installation, registration, intro screens, help, contents, credits, exit, navigation etc.)

- Hold midpoint review meeting

- Present to select program staff for buy-in/feedback

- Determine required collateral material

- Get ballpark estimates for printing final collateral materials

- Review Budget

- Review Schedule

- Identify Field test sites and begin planning for field test

- Finalize all specs

- First draft text/graphics

- Produce sound/video/interactive elements/

- Approve final graphics

- Deliver final text to vendor

# Alpha Development

- 1st draft of text within graphic user interface (functionality not all in place) Vendor must supply style sheet.

- Draft of collateral material

- Launch Alpha version (all functionality)

- Review Alpha version

- Quality Assurance Testing (opportunity 1)

- Draft user docs

# Beta Development

- Make changes to content/fix bugs from Alpha

- Launch Beta version

- Quality Assurance Testing (opportunity 2)

- Prepare final draft version of collateral material (if needed for field test)

- Field Test

# Final Production

- Review Budget

- Review Schedule

- Design final collateral materials

- Revisions based on field test feedback

- Quality Assurance testing (opportunity 3)

- Get bids for final production of collateral materials  (i.e., CD duplication, package, printing, etc.)

- Proof and review collateral materials

- Send Glass Master for Duplicating of CDs

- Send files to printer

- Collate final package

- Final launch of site

- Ship materials

- Publicity

# Copy

Title Screen

Intro Screens: Registration, Sound, new and registered user entry, etc)

Help

Main Menu Screen

Dropdown menus

Main content

Credits

Exit Screen

User Docs: Guidelines for use, Installation Instructions, Troubleshooting Guide

System Requirements

Licensing Agreement

CD Label

Outer Packaging (FC, BC, IFC, IBC, Spine)

Manual cover (FC, BC, IFC, IBC, Spine)

Manual Text

Index

Glossary

# Graphics/Design

Buttons

Page Design/User Interface

Special Elements

Content Graphics

Color and font palette

To be determined up front:

System Requirements

Separate tracks (i.e., field, level of staff, geography, etc)

Registration

Intro material

Installations

Help

Navigation

Main Menu

Exit

Credits

New Log-on capability

Data collection ability

Management of Data

Evaluation

Final package:

Get ISBNs

Paperwork for software used in development (i.e., Quicktime, Macromedia, etc.)

Collect required logos for software used.

Determine Quantities

Determine Selling price

Determine Shipping Instructions

Assign PO number for shipments to the warehouse.

Publicity: