## Project Estimation Worksheet

This is a relatively crude worksheet for estimating project scope. This "Project Estimation Worksheet" will provide you with some guidance for setting up your own spreadsheet program to calculate the temporal, financial, and personnel resources required for a interactive multimedia design project.

| # Types of Materials | Number of pages/items | # Amount of instruction | Development time* |
| --- | --- | --- | --- |
| # Readings |  | (approx. 20 pages/hr) | (approx. 1 page/hr) |
| - Handouts |  |  |  |
| - Content (Static text) |  |  |  |
| - Workbook pages |  |  |  |
| - Other (specify) |  |  |  |
| ## Video |  | (Script = 2 pages./min. Storyboard = variable) | (Script = 1 page/1.5 hr. ### Storyboard =2 bds/hr.) |
| - Script |  |  |  |
| - Storyboard |  |  |  |
| ### Audio |  | (1.3 pages/min.) | (1 page/hr.) |
| - Script |  |  |  |
| # Interactive Media |  | (Format sheet=10 per min Storyboard = variable Intro/summary=½ page per) | (Format sheet=4 per hr. Storyboard =2 bds/hr. Intro/summary=1 per hr) |
| - Format sheets |  |  |  |
| - Storyboards |  |  |  |
| - Intros/Summaries |  |  |  |
| Instructor Materials |  | #### (Orientation = 10–15 pages #### Lesson plans = 1 per session ### Slides/Transps = 10 per hr) | (Orientation = 1 page/hr. Lesson plans=10 hrs per #### Slides/Transp=2 per hr) |
| - Orientation |  |  |  |
| - Lesson plans |  |  |  |
| - Slides/Transps |  |  |  |
| ##### Assessment Materials |  | #### (Exercises = <5 pages per #### Tests = variable) | #### (Exercises = 5hrs per Tests = 2 per hr) |
| - Exercises |  |  |  |
| - Tests |  |  |  |

* Increase estimates by 50% for inexperienced writers/instructional designers

Adapted from: Greer, M. (1992). ID Project Management: Tools and techniques for instructional designers and developers.  Englewood Cliffs, NJ: Educational Technology.